Murton Parish Neighbourhood Plan

An update… April 14th 2024

I have now heard from the CYC Strategic Planning Group giving some more suggestions to sharpen the policy statements.  They call these suggestions ‘light touches’.  They have also offered to look after the production of the maps and to help with the final layout and formatting.

There has been an unfortunate delay of two months.  They sent a long document to me in February giving comments on our latest draft of the Submission Plan which I never noted.  I must have deleted it unread as I have no record of it.  This is unfortunate but I hope that we can catch up a little.

There have been two events since we sent our Plan to CYC.  One is a revision to the National Planning Policy Framework in late 2023 and the other are changes to the draft Local Plan following the hearing sessions by the Inspectors during 2023. We now await the Inspectors Report.  All this means that we have to check every reference we have made to these two Plans to ensure that we are conforming to the latest versions.

So, the MPNP is alive and well and still needing a lot of work done to it.

April14th 2024