Murton Parish Neighbourhood Plan Working Party

Report to the Murton Parish Council meeting on February 10th 2021

- Maps for the Neighbourhood Plan

We noted in our January 13th 2021 report that we still awaited the maps which CYC officers are preparing for our three major reports, the Plan, the SEA (Strategic Environmental Assessment) and HRA (Habitats Regulations Assessment).  Unfortunately, they still have not been done in spite of multiple requests as much of the Local Plan needs much more work on it and understandably, in comparison we are not a priority). We have now written suggesting that we do not have so many maps and that we refer the reader to maps produced in CYC reports, for example in the emerging Local Plan. This is definitely second best but we do not want to hold up the pre-submission draft for consultation phase any longer.

- The pre-submission draft for consultation

We had hoped to have started the public consultation this month, for a six-week period.  However, this depended on the CYC providing us with the maps to illustrate the Plan.  It also needs for us to have lists of names and address of businesses landowners and other stakeholders in the Parish so that we can send them the necessary documentation.  CYC has promised to supply these.

- Printing

Although we will publish all papers on line, we need to print and distribute the pre-consultation pamphlet for widespread distribution (2 above) and we also need to print multiple copies of the three major documents.  We are asking for advice from two parishes that have recently gone through the process (Heslington and Huntington) for advice on numbers.

- Overall

Although these is a lot of tidying up to do, the vast bulk of the work on the here major documents has been done.